## Executive Summary
Worktop - API Test Intelligence Platform
Tentative 5-Week MVP Development Plan ¦ Spring Boot + REST Assured
Audience: stakeholders, customer sponsors, product, and engineering leadership
MVP At A Glance
Plan Duration | 5 weeks | 10 Jul 2026 - 13 Aug 2026
Team Size | 2 developers | Focused MVP squad
Primary MVP | REST Assured | Weeks 1-3
Extensions | GraphQL + gRPC | Weeks 4-5
Customer Value Narrative
Foundation first | The platform starts by understanding API stories, repository structure, existing tests, reusable builders, mocks, DTOs, controllers, and service dependencies before generating tests.
Repository-native generation | REST Assured tests are generated to match project conventions and reuse existing fixtures, utilities, and test patterns instead of creating isolated generic tests.
Validation-led MVP | The REST MVP is validated through pilot repositories using compilation, execution, reuse, and quality metrics before expanding into GraphQL and gRPC.
Reusable platform foundation | GraphQL and gRPC support are positioned as protocol extensions over the same intelligence, generation, validation, and reporting foundation.
Executive Milestones
Milestone | Target | Customer-Visible Outcome
Discovery foundation ready | Week 1 | API catalog, dependency map, and reuse intelligence are available.
REST Assured generation ready | Week 2 | Repository-native REST Assured test suite can be generated and structurally validated.
REST MVP release candidate | Week 3 | Pilot validation results and MVP documentation are available.
GraphQL MVP extension | Week 4 | GraphQL scenarios and integration tests can be generated.
gRPC MVP extension | Week 5 | Unary gRPC scenarios and integration tests can be generated.

## 5-Week Roadmap
5-Week MVP Roadmap
Clear weekly plan from REST Assured MVP foundation through GraphQL and gRPC extensions
Week | Start Date | End Date | Developers | Phase | Focus Area | Problem We Are Solving | Scope Summary | Key Deliverables
Week 1 | 2026-07-10 | 2026-07-16 | 2 | Foundation | API Story & Repository Intelligence Foundation | Understand API stories and repository structure before generating tests, enabling repository-aware and reusable test generation. | • Analyze API user stories and acceptance criteria. • Discover Spring Boot project structure, Gradle/Maven configuration, and Java version. • Identify REST controllers, endpoints, DTOs, and WebClient integrations. • Analyze architecture, package conventions, and module structure. • Discover existing REST Assured tests, builders, fixtures, mocks, utilities, and reusable assets. | • API Story Intelligence Report • Repository Discovery Engine • Project Profile Report • Architecture & Dependency Report • REST API Catalog • WebClient Dependency Map • Existing Test & Reuse Intelligence Report
Week 2 | 2026-07-17 | 2026-07-23 | 2 | Generation | Scenario Intelligence & REST Assured Generation | Convert repository and story intelligence into executable repository-native REST Assured integration tests. | • Analyze source code changes and impacted APIs. • Generate positive, negative, validation, authorization, and error-handling scenarios. • Classify tests for CI or Stage execution. • Generate REST Assured tests following repository conventions and maximize reuse of existing assets. • Perform structural and compilation validation. | • Change Intelligence Engine • Scenario Generation Engine • Execution Classification Engine (CI/Stage) • REST Assured Test Generator • Generated REST Assured Test Suite • Validation & Generation Report
Week 3 | 2026-07-24 | 2026-07-30 | 2 | REST MVP | REST Assured MVP Validation | Complete the end-to-end REST Assured MVP and validate generation across pilot repositories. | • Execute complete generation workflow. • Validate generated tests on pilot repositories. • Measure generation quality, compilation success, execution success, and asset reuse. • Finalize MVP documentation and benchmark results. | • REST Assured MVP Release Candidate • End-to-End Generation Pipeline • Pilot Validation Results • Repository Compatibility Report • Benchmark & Metrics Report • MVP Documentation
Week 4 | 2026-07-31 | 2026-08-06 | 2 | GraphQL MVP | GraphQL Intelligence (MVP) | Extend the API Intelligence platform to understand and generate tests for GraphQL repositories using the same core intelligence pipeline. | • Discover GraphQL schemas, queries, mutations, and resolvers. • Generate GraphQL-specific scenarios and assertions. • Produce repository-native GraphQL integration tests. • Reuse existing discovery, validation, reporting, and execution framework. | • GraphQL Discovery Engine • Schema & Resolver Analyzer • GraphQL Scenario Generator • GraphQL Test Generator • GraphQL Validation Report
Week 5 | 2026-08-07 | 2026-08-13 | 2 | gRPC MVP | gRPC Intelligence (MVP) | Extend API Intelligence to support repositories exposing gRPC services while leveraging the shared platform foundation. | • Discover Protocol Buffer (.proto) files. • Analyze services, RPC methods, request/response messages, and generated stubs. • Generate unary gRPC scenarios and assertions. • Produce repository-native gRPC integration tests using the existing intelligence framework. | • gRPC Discovery Engine • Protocol Buffer Analyzer • RPC Scenario Generator • gRPC Test Generator • gRPC Validation Report

## Weekly Details
Weekly Detail View
Expanded narrative for planning conversations and customer alignment
Week | Phase | Focus | Workstream Detail | Success Outcome
Week 1 Jul 10, 2026 - Jul 16, 2026 | Foundation | API Story & Repository Intelligence Foundation | • Analyze API user stories and acceptance criteria. • Discover Spring Boot project structure, Gradle/Maven configuration, and Java version. • Identify REST controllers, endpoints, DTOs, and WebClient integrations. • Analyze architecture, package conventions, and module structure. • Discover existing REST Assured tests, builders, fixtures, mocks, utilities, and reusable assets. | Repository-aware API intelligence baseline with clear reuse opportunities and endpoint coverage map.
Week 2 Jul 17, 2026 - Jul 23, 2026 | Generation | Scenario Intelligence & REST Assured Generation | • Analyze source code changes and impacted APIs. • Generate positive, negative, validation, authorization, and error-handling scenarios. • Classify tests for CI or Stage execution. • Generate REST Assured tests following repository conventions and maximize reuse of existing assets. • Perform structural and compilation validation. | Executable REST Assured tests generated with repository conventions, reuse, and validation feedback.
Week 3 Jul 24, 2026 - Jul 30, 2026 | REST MVP | REST Assured MVP Validation | • Execute complete generation workflow. • Validate generated tests on pilot repositories. • Measure generation quality, compilation success, execution success, and asset reuse. • Finalize MVP documentation and benchmark results. | Validated REST Assured MVP release candidate with quality metrics and pilot compatibility evidence.
Week 4 Jul 31, 2026 - Aug 06, 2026 | GraphQL MVP | GraphQL Intelligence (MVP) | • Discover GraphQL schemas, queries, mutations, and resolvers. • Generate GraphQL-specific scenarios and assertions. • Produce repository-native GraphQL integration tests. • Reuse existing discovery, validation, reporting, and execution framework. | GraphQL MVP extension using the same API intelligence foundation and generation workflow.
Week 5 Aug 07, 2026 - Aug 13, 2026 | gRPC MVP | gRPC Intelligence (MVP) | • Discover Protocol Buffer (.proto) files. • Analyze services, RPC methods, request/response messages, and generated stubs. • Generate unary gRPC scenarios and assertions. • Produce repository-native gRPC integration tests using the existing intelligence framework. | gRPC MVP extension demonstrating shared foundation reuse across service protocols.

## Deliverables
Deliverables Register
Trackable outputs for stakeholder and customer review
Week | Phase | Deliverable | Category | Target Date | Status
Week 1 | Foundation | API Story Intelligence Report | Stakeholder Evidence | 2026-07-16 | Planned
Week 1 | Foundation | Repository Discovery Engine | Platform Capability | 2026-07-16 | Planned
Week 1 | Foundation | Project Profile Report | Stakeholder Evidence | 2026-07-16 | Planned
Week 1 | Foundation | Architecture & Dependency Report | Stakeholder Evidence | 2026-07-16 | Planned
Week 1 | Foundation | REST API Catalog | MVP Output | 2026-07-16 | Planned
Week 1 | Foundation | WebClient Dependency Map | MVP Output | 2026-07-16 | Planned
Week 1 | Foundation | Existing Test & Reuse Intelligence Report | Stakeholder Evidence | 2026-07-16 | Planned
Week 2 | Generation | Change Intelligence Engine | Platform Capability | 2026-07-23 | Planned
Week 2 | Generation | Scenario Generation Engine | Platform Capability | 2026-07-23 | Planned
Week 2 | Generation | Execution Classification Engine (CI/Stage) | Platform Capability | 2026-07-23 | Planned
Week 2 | Generation | REST Assured Test Generator | Platform Capability | 2026-07-23 | Planned
Week 2 | Generation | Generated REST Assured Test Suite | Executable Asset | 2026-07-23 | Planned
Week 2 | Generation | Validation & Generation Report | Stakeholder Evidence | 2026-07-23 | Planned
Week 3 | REST MVP | REST Assured MVP Release Candidate | MVP Output | 2026-07-30 | Planned
Week 3 | REST MVP | End-to-End Generation Pipeline | Executable Asset | 2026-07-30 | Planned
Week 3 | REST MVP | Pilot Validation Results | Stakeholder Evidence | 2026-07-30 | Planned
Week 3 | REST MVP | Repository Compatibility Report | Stakeholder Evidence | 2026-07-30 | Planned
Week 3 | REST MVP | Benchmark & Metrics Report | Stakeholder Evidence | 2026-07-30 | Planned
Week 3 | REST MVP | MVP Documentation | Enablement | 2026-07-30 | Planned
Week 4 | GraphQL MVP | GraphQL Discovery Engine | Platform Capability | 2026-08-06 | Planned
Week 4 | GraphQL MVP | Schema & Resolver Analyzer | MVP Output | 2026-08-06 | Planned
Week 4 | GraphQL MVP | GraphQL Scenario Generator | Platform Capability | 2026-08-06 | Planned
Week 4 | GraphQL MVP | GraphQL Test Generator | Platform Capability | 2026-08-06 | Planned
Week 4 | GraphQL MVP | GraphQL Validation Report | Stakeholder Evidence | 2026-08-06 | Planned
Week 5 | gRPC MVP | gRPC Discovery Engine | Platform Capability | 2026-08-13 | Planned
Week 5 | gRPC MVP | Protocol Buffer Analyzer | MVP Output | 2026-08-13 | Planned
Week 5 | gRPC MVP | RPC Scenario Generator | Platform Capability | 2026-08-13 | Planned
Week 5 | gRPC MVP | gRPC Test Generator | Platform Capability | 2026-08-13 | Planned
Week 5 | gRPC MVP | gRPC Validation Report | Stakeholder Evidence | 2026-08-13 | Planned

## Assumptions & Scope
Assumptions, Scope Notes & MVP Boundaries
Use this sheet to align expectations before delivery begins
Topic | Clarification
Roadmap status | Tentative MVP planning roadmap; dates and scope should be confirmed against team availability and customer priorities.
Weeks 1-3 | Establish reusable API Test Intelligence foundation and deliver the REST Assured MVP.
Weeks 4-5 | Demonstrate platform extension to GraphQL and gRPC using the same core intelligence architecture.
Out of scope for MVP | Production hardening, performance optimization, broad repository validation, and long-running stabilization.
Team | 2 developers focused on Spring Boot, REST Assured, GraphQL, and gRPC API test generation workflows.
Recommended Next Phase
Production hardening | Stabilize prompts, schema contracts, validation, retry/recovery, test execution reliability, and repository-specific edge cases.
Performance and scalability | Optimize repository scanning, source intelligence, generation latency, and large-monorepo handling.
Broader validation | Run against a wider repository portfolio and convert learnings into reusable compatibility profiles.